# The 30-Day Rollout Timeline

HIPAA Training Rollout Template  |  HIPAA Training US  |  hipaatraining.us

Adjust the dates to your size, but keep the shape: preplanning front-loaded, the launch backed by leadership, follow-up relentless. Day 0 = launch day.

## Days −14 to −8  ·  Preplanning

- Build the complete roster (everyone who could touch PHI)

- Segment by work pattern (shifts, part-time, field, remote)

- Lock in affordable per-everyone pricing so no one is rationed

- Choose your completion-tracking method and assign one owner

## Days −7 to −1  ·  Executive alignment

- Brief leadership; secure their commitment to go first

- Draft the announcement in the executive’s voice

- Schedule any live beginner sessions for new hires

## Day 0  ·  Launch

- Executive announcement goes out: link, deadline, clear “why”

- New hires and edge roles routed to their specific tracks

## Days 1–3

- Leadership and managers complete training and visibly model it

## Days 4–7

- First reminder with running completion stats

- Live beginner session held for new-to-healthcare staff

## Days 8–14

- Escalating reminders; managers looped in for their teams

- Protected time offered for genuine scheduling conflicts

## Days 15–21

- Direct manager follow-up for the final stragglers

- Couriers and field staff confirmed complete

## Days 22–30

- Verify 100%; capture and file every completion record

- Recognize milestones; set the date for next year’s training